## Blad1
DAGBOEK PROJECTWERK |  | AUTHORS: | PIETER DELOBELLE, ANTON DANNEELS, MATTHIAS DE LANGE
|  | UPDATE: | 2017-03-02
DAY | TASK | STATUS
2016-11-14 | Projectweek | COMPLETED
2016-11-15 | Projectweek | COMPLETED
2016-11-16 | Projectweek | COMPLETED
2016-11-17 | Projectweek | COMPLETED
2016-11-18 | Projectweek | COMPLETED
2016-11-27 | Indienen verslag projectweek | COMPLETED
2017-02-14 | Opnieuw opnemen van project | COMPLETED
2017-02-20 | Persistence context configureren | ON TRACK
2017-02-23 | Instellen VM, start conversie model -> database | COMPLETED
2017-02-24 | Instellen VM, start conversie model -> database | COMPLETED
2017-02-25 | Start MatlabProcessor | COMPLETED
2017-02-26 | MatlabProcessor klaar | COMPLETED
2017-02-27 | Overleg en taakverdeling authenticatie en front-end | COMPLETED
2017-02-28 | Authenticatie | ON TRACK
2017-02-01 | Authenticatie | ON TRACK
2017-02-02 | Authenticatie | COMPLETED